## Customer Information
NovaCRM – New Customer Onboarding
How to use: make a copy per customer. Fill the yellow cells (most are pre-filled by the Intake & Communication agents). Grey cells are calculated. Column C shows an example of the expected format.
Field | Value | Example (format) | Source / notes
Customer (company) name |  | Acme Corp | Deal email – Agent 1
Customer primary contact name |  | Jane Doe | Deal email – Agent 1
Customer primary contact email |  | jane.doe@acme.com | Deal email – Agent 1; invited to Slack
Account Executive (AE) |  | Raj Kumar | Deal email – Agent 1
AE email |  | raj.kumar@novacrm.com | Sender of the deal email
AE phone (E.164) |  | +919876543210 | AE directory – used for the tier call
Salesforce opportunity link |  | https://novacrm.my.salesforce.com/006XXXXXXXXXXXX | Deal email – required field
Signed Order Form link(s) |  | https://drive.example.com/acme-order-form.pdf | AE / Deal desk
Plan tier |  | Enterprise | Confirmed by AE on the phone – never guessed
Tier confirmed via |  | Voice call | Voice call (Agent 1) or Manual (CS Manager)
Tier confirmed on |  | 2026-10-07 | Date of confirmation
Onboarding duration (days) |  | 30 | Enterprise 30 / Growth 14
CSM model |  | Dedicated CSM | Enterprise dedicated / Growth pooled
CSM – Rocketlane Project Owner |  | Asha Menon | Gets 4-day overdue escalations
CS Manager – Rocketlane Project Manager |  | Priya | Gets 1-day overdue escalations
Onboarding start date |  | 2026-10-08 | Rocketlane project start
Target go-live / end date |  | 2026-11-06 | Start + duration − 1
Rocketlane project link |  | https://novacrm.rocketlane.com/projects/4242 | Created by Agent 1
Shared Slack channel |  | #nova-ent-acme-corp | Created by Agent 2
Kickoff call date |  | 2026-10-10 | Task 13
Data migration signed off by (customer name, date) |  | Jane Doe, 2026-10-22 | Task 19 – required before Go-Live
Ongoing support owner after handoff |  | Support team – EMEA pod | Task 27
Note on B13: Only set after the AE explicitly confirms the tier (voice call read-back) or a CS Manager sets it manually.

## Onboarding Checklist
Onboarding Checklist
Customer |  | 0 |  | Tasks | 30 |  | Legend: yellow = fill in · grey = calculated · Done by in blue = done automatically by an agent (just verify).
Plan tier |  | 0 |  | Done / N/A | 0 |  | Due date = start date + the tier's day offset. Rows turn red when overdue, amber when Blocked.
Start date |  | 0 |  | % complete | 0%
Target go-live / end |  |  |  | Overdue | 0
|  |  |  | Blocked | 0
# | Phase | Task | Details / checklist | Owner | Done by | In Rocketlane template | Enterprise day | Growth day | Due date | Status | Completed on | Link / evidence | Notes
1 | 0. Intake & Setup | Receive deal notification email from AE | Detected in the CS inbox (Gmail → Pub/Sub); closed-deal email validated | Agent 1 | Agent 1 – Intake (auto) | No | 0 | 0 |  | Not started
2 | 0. Intake & Setup | Validate required deal details | Customer name · contact email · AE name/email · Salesforce opportunity link. If anything is missing: email the AE and wait – never guess | Agent 1 | Agent 1 – Intake (auto) | No | 0 | 0 |  | Not started
3 | 0. Intake & Setup | Confirm plan tier with the AE by phone | Ask Enterprise or Growth → read back → AE confirms. Retry up to 3× in AE working hours, then escalate to CS Manager | Agent 1 / CS Manager | Agent 1 – Intake (auto) | No | 0 | 0 |  | Not started
4 | 0. Intake & Setup | Complete the Customer Information tab | Check every pre-filled field; fill any gaps | CSM | Manual | No | 1 | 1 |  | Not started
5 | 0. Intake & Setup | Insert links to Salesforce opportunity and signed Order Form(s) | Add to Customer Information and the Rocketlane project | CSM / AE | Manual | No | 1 | 1 |  | Not started
6 | 0. Intake & Setup | Create Rocketlane project from the tier template | Enterprise 30-day or Growth 14-day template, chosen from the confirmed tier | Agent 1 | Agent 1 – Intake (auto) | No | 0 | 0 |  | Not started
7 | 0. Intake & Setup | Assign Project Owner (CSM) and Project Manager (CS Manager) | Enterprise: dedicated CSM · Growth: CSM from the pool. Both must be set for overdue escalations to work | Agent 1 | Agent 1 – Intake (auto) | No | 0 | 0 |  | Not started
8 | 0. Intake & Setup | Create shared Slack channel with tier-specific name, topic and welcome message | Channel name/topic/welcome personalised by tier and customer | Agent 2 | Agent 2 – Communication (auto) | No | 0 | 0 |  | Not started
9 | 0. Intake & Setup | Invite customer contact to the Slack channel | Slack Connect invite sent · confirm the customer joined | Agent 2 / CSM | Agent 2 – Communication (auto) | No | 1 | 1 |  | Not started
10 | 0. Intake & Setup | Internal handover call AE → CSM | Deal context · stakeholders · commitments made in the sales cycle · risks | CSM | Manual | No | 2 | 1 |  | Not started
11 | 0. Intake & Setup | Verify the Rocketlane project set-up | Correct template and dates · owner & manager set · overdue escalation automation active | CS Manager | Manual | No | 2 | 1 |  | Not started
12 | 1. Kickoff | Schedule kickoff call | Invite customer stakeholders · share agenda | CSM | Manual | Yes | 3 | 2 |  | Not started
13 | 1. Kickoff | Hold kickoff call ★ milestone | Introductions · plan walkthrough · roles · ways of working · record attendees | CSM | Manual | Yes | 4 | 2 |  | Not started
14 | 1. Kickoff | Confirm success criteria, stakeholders and go-live date | 3–5 success criteria · customer stakeholders · agreed go-live date · data sources to migrate | CSM + Customer | Manual | Yes | 5 | 3 |  | Not started
15 | 2. Data Migration | Provide data export | Contacts, accounts, deals, activities · secure share link · expected record counts | Customer | Manual | Yes | 7 | 4 |  | Not started
16 | 2. Data Migration | Field mapping and data cleanup | Map fields to NovaCRM · flag duplicates/bad data · customer approves the mapping | CSM | Manual | Yes | 10 | 5 |  | Not started
17 | 2. Data Migration | Test import in sandbox | Sample import · check fields, owners, pipeline stages · fix mapping issues | CSM | Manual | Yes | 12 | 6 |  | Not started
18 | 2. Data Migration | Production import | Full import · record imported counts per object · share import summary with customer | CSM | Manual | Yes | 14 | 7 |  | Not started
19 | 2. Data Migration | Customer data verification and sign-off ★ milestone | Record counts match source · 20-record spot check · owners & stages correct · attachments/notes present · customer confirms in writing. GO-LIVE IS BLOCKED UNTIL THIS IS DONE | Customer | Manual | Yes | 16 | 8 |  | Not started
20 | 3. Configuration | Users, roles and permissions | Create users · assign roles · teams/territories | CSM | Manual | Yes | 12 | 6 |  | Not started
21 | 3. Configuration | Pipelines, custom fields and automations | Enterprise: custom set-up · Growth: standard set | CSM | Manual | Yes | 17 | 8 |  | Not started
22 | 3. Configuration | Integrations | Email & calendar sync · Enterprise: other agreed integrations · test each | CSM | Manual | Yes | 19 | 9 |  | Not started
23 | 3. Configuration | Admin and end-user training | Enterprise: role-based sessions · Growth: one group session · share recordings | CSM | Manual | Yes | 23 | 10 |  | Not started
24 | 4. Go-Live | Go-live readiness check and launch ★ milestone | Data signed off (task 19) · training done · integrations tested · customer approves go-live | CSM | Manual | Yes | 25 | 11 |  | Not started
25 | 4. Go-Live | Hypercare check-ins | Daily issue check · resolve blockers · confirm adoption (logins, records created) | CSM | Manual | Yes | 28 | 13 |  | Not started
26 | 5. Handoff & Close | Write handoff summary ★ milestone | Goals & success criteria · configuration · integrations · open issues · key contacts | CSM | Manual | Yes | 29 | 14 |  | Not started
27 | 5. Handoff & Close | Handoff call with Support; move customer to ongoing support | Introduce support owner · transfer open items · update account status in Salesforce | CSM + CS Manager | Manual | Yes | 30 | 14 |  | Not started
28 | 5. Handoff & Close | Send onboarding satisfaction survey | CSAT / short feedback form to the customer contact | CSM | Manual | No | 30 | 14 |  | Not started
29 | 5. Handoff & Close | Close the Rocketlane project | All tasks done or N/A · project marked complete | CS Manager | Manual | No | 30 | 14 |  | Not started
30 | 5. Handoff & Close | Share the go-live win internally | Post in the team's wins channel (customer, tier, days to go-live) | CSM | Manual | No | 30 | 14 |  | Not started

## Tier Differences
Enterprise vs Growth
Aspect | Enterprise | Growth
Onboarding length | 30 days | 14 days
CSM model | Dedicated CSM | Pooled CSM
Rocketlane template | NovaCRM Onboarding – Enterprise (30d) | NovaCRM Onboarding – Growth (14d)
Slack channel name | nova-ent-<customer> | nova-<customer>
Kickoff | Kickoff call by day 4 | Kickoff call by day 2
Data migration | Full migration incl. activities; sandbox test | Core objects; sandbox test
Configuration | Custom pipelines, fields and automations | Standard configuration set
Integrations | Email/calendar + agreed custom integrations | Email/calendar sync
Training | Role-based sessions (admins, managers, reps) | One group session + recordings
Hypercare | 3 days | 2 days
Data sign-off before go-live | Required (customer) | Required (customer)

## Escalation & Guardrails
Escalation rules and guardrails
Rule | Where | Trigger | Action
Overdue – level 1 | Rocketlane automation (both templates) | Task overdue by 1 day | Notify the Project Manager (CS Manager)
Overdue – level 2 | Rocketlane automation (both templates) | Task overdue by 4 days | Notify the Project Owner (CSM)
Blocked task (assumption – to confirm) | Process / Rocketlane | Task status Blocked for more than 3 days | CSM flags it in Rocketlane; CS Manager reviews blocked tasks daily. Open question to Rocketlane: should blocked-but-not-overdue tasks also escalate?
Missing deal details | Agent 1 | Required field missing in the AE's email | Ask the AE for the missing details; no project until complete
Plan tier not confirmed | Agent 1 | No answer / unclear / no read-back after 3 calls | Escalate to CS Manager to set the tier manually; never assume a tier
Data not verified | Checklist task 19 / Rocketlane dependency | Go-live attempted before customer data sign-off | Go-live task is blocked by the dependency on task 19
Wrong template | Agent 1 + plan tier config | Template chosen manually | Template always comes from the confirmed tier; CS Manager verifies in task 11
Audit trail | All agents | Every agent action | Logged with timestamp, inputs, outputs and decision rationale